# Event Security Action Plan

# Pre-Planning the Event

## Review the dates of the event.

## Determine how many people expected to attend the events.

## Identify if it is open to the general public or membership only.

## Discuss all facilities to be used for the event.

# Physical Security Setup

## Conduct walk-through to determine how much security is needed at the different facilities.

## Obtain a list of contract security companies that are cleared to work in the Convention Center and other venues.

## Contact local police department, Sheriff’s Department and other appropriate support entities.  (i.e., Convention Center Security, Hotel Security, Contract Security, Fire Marshall and EMT Service – based on the number of attendees).

## Contact Law Enforcement agencies to see who is eligible for off-duty work.  Obtain a contact liaison to coordinate scheduling off-duty support.

## Obtain maps and/or blueprints of the facilities that will be used.

## Establish access control procedures (i.e., Convention Center/Hotel).

# Executive Protection

## Establish number of people needing protection.

## Review itinerary information in detail.

## Conduct a walk-through of all temporary accommodations.

## Identify closest hospitals/emergency facilities.

## Obtain list of all events the Executive(s) will attend.

# Advance On-site Planning with Security

## Contact all parties involved with notification of “count-down” meeting.

## Distribute agenda and other non-sensitive written information prior to meeting.

## Conduct meeting with ample time for Q & A.

## Confirm that all parties are fully aware of their role.

# After-Action Meeting with Representatives from Each Department/Entity Involved

## Open meeting with a thank you.

## Critique successes and challenges (Exchange of Information).

## Make specific follow-up plans for next event.

Submitted by National Rifle Association